| 2025 GA 505 Continuum of Care Homeless Assistance Grant Competition Process and Timeline |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Event/ Activity | Responsible | Date/Time | Place | Notes |
| NOFA released | HUD | 11/13/2025 | HUD | HUD releases the Notice of Funding Availability |
| Collaborative and Project Applications Release | HUD | TBD | ESNAPS HUD Exchange | Hud releases Collaborative and Project Applications The Collaborative and Project Applications have not yet been posted to the Continuum of Care Competition Page. Interested parties are encouraged to regularly check the Competition Page at this link for updates: Continuum of Care Program ¦ HUD.gov / U.S. Department of Housing and Urban Development (HUD) |
| Organizations wishing to submit a project application in the 2025 CoC Competition must attend the Technical Assistance Workshop. Applications will not be accepted from organizations who did not attend a Technical Assistance Workshop |  |  |  |  |  |
| Technical Assistance Workshop MANDATORY for New and Renewal Applications | Application Committee | 12/1/2025 2-4 PM | Via Zoom (LINK IN NOTES COLUMN) | Release information about local priorities and HUD guidelines for proposals. Agencies will be given an electronic proposal package and training on how to complete the application. https://us02web.zoom.us/j/85873415643?pwd=bcep6v5k12YcfGrVOZ7fliqNeEbuor.1 Meeting ID: 858 7341 5643 Passcode: 379013 |
| Agencies write project proposals | Agencies | 12/01/2025 to 12/12/2025 | Various | All agencies seeking CoC funding must have applications turned in to CoC via ESNAPS by 12 noon on 12/12/2025 |
| Rank & Review Panel Training | Collaborative Applicant | 12/10/2025 9 AM | United Way | Rank & Review Panel receives training for scoring projects. |
| Community’s CoC Application is written | Application Committee/ Project Leads | 12/1/2025 to 1/12/2025 | Various | Application committee as well as project leads will divide application and write it collaboratively |
| Project proposals are due in ESNAPS | Agencies | 12/12/2025 NOON | ESNAPS | See Proposal Submission Checklist for list of required documents and information about where and how to turn in documents. |
| Rank & Review Panel reviews project proposals | Review and Rank Panel | 12/12/2025 to 12/15/2025 | Various | Rank & Review Panel reads and scores proposals independently. |
| Rank & Review Panel meets | Collaborative Applicant | 12/15/2025 9 AM | United Way | Rank & Review Panel meets to discuss proposals and determine how projects will be ranked in the 2025 application. |
| Posting of Preliminary Ranked List | Collaborative Applicant | 12/15/2025 | Email and HFG/CoC website | Preliminary priority list emailed to agencies and posted to website |
| Applicant Appeals due | Agencies | 12/17/2025 5PM | Email to HFG | Agencies may inspect their scores and formulate a written appeal based on appeal policy. |
| Appeals Reviewed as needed | Review and rank Panel | 12/19/2025 9 AM | United Way | Review appeals and recalculates scores, if necessary. |
| Posting of Ranked List After 1 Appeal | Collaborative Applicant | 12/19/2025 | Email and HFG/CoC website | Priority list after appeal 1 emailed to agencies. |
| Applicant Appeals due | Agencies | 12/22/2025 12 NOON | Email to HFG | Agencies may inspect their scores and formulate a written appeal based on appeal policy. |
| Appeals Reviewed as needed | Review and rank Panel | 12/22/2025 2 PM | United Way | Review appeals and recalculates scores, if necessary. |
| Posting of Ranked List After 2 Appeal | Collaborative Applicant | 12/22/2025 | Email and HFG/CoC website | Priority list after appeal 2 emailed to agencies. |
| Final ranked list is distributed to applicants | Collaborative Applicant | 12/22/2025 | Email and HFG/CoC website | Final priority list to be emailed to CoC Board for approval and emailed to applicants. |
| CoC Board Vote to Approve Ranking | Collaborative Applicant & CoC Board | 12/22/2025 Vote Due 12/23/2025 by 12 NOON | Via email | Final Priority List recommendation is sent to CoC Board for approval. |
| CoC Board Vote to be posted | Collaborative Applicant & CoC Board | 12/23/2025 | Via Email and HFG/CoC Website | Final Priority List published on HFG/CoC website and emailed to applicants. |
| CoC Consolidated Application Posting | Application Committee | 01/09/2025 | Email and HFG/CoC website | CoC consolidated application is posted on CoC website |
| CoC Consolidated Application Local Deadline |  | 01/12/2025 | ESNAPS | Application is packaged and submitted to HUD. |
| Application is due to HUD |  | 01/14/2025 8 PM | ESNAPS | APPLICATION MUST BE SUBMITTED BY 8 PM |

Meetings/Trainings, Project Deadlines, Community Deadlines				11/17/2025